## Sheet1
WORKFLOW AND RESPONSIBILITIES
majour task and responsible team member | implementig object types | implementig majour UI logic (Veso) | implementing controlers(Joro) | detailed implementation of specific pages (Rosi and Yordan) | detailed unit tests implementation (Rosi and Yordan) | host application on http://rawgit.com (Geri)
specific task and responsible team member | Track (Geri) | start page / search | logInControler | player page
| Playlist (Geri) | style gude (for all pages) | playlistControler | manage playlist page
| User (Geri) |  | playerControler | profile page
| PlaylistCollection (Veso) |  |  | log in page
expected end | 29.08.2015 | 30.08.2015 | 01.09.2015 | 02.09.2015 | 02.09.2015 | 03.09.2015